## Sheet1
New Server Implementatons
# | Item | Projected Date | Status
1 | Old Server Checkup | - | Completed
2 | Old server virus checkup | To be filled | Completed
3 | Old server sources external virus checkup | To be filled | TAR is ready. Need to be scanned by your team
4 | New server Software Installations | 2014-02-12 | Almost done
5 | New sever antivirus installation | 2014-02-12 | Completed
6 | New server firewall and security setup | 2014-05-12 | 50% done
7 | New server site configurations as per old server | 8-9/12/2014 | To be filled
8 | Logging software instlallation if any | 10-11/12/2014 | To be filled
9 | Handover | 16-17/12/2014 | After your confirmation on testing of sites on new server